AQLIO DELIVERY MILESTONE

# M0 — First Useful Deployment

Implementation package for the “Ask My Documents” vertical slice

| Field | Decision |
| --- | --- |
| Milestone outcome | A new non-technical user creates, deploys, and shares a useful document Q&A assistant. |
| Visible journey | Create Project → Add Documents → Preview → Deploy → Share |
| Hidden by design | GitHub, Railway, API keys, model/provider selection, repositories, CI/CD, containers, and infrastructure configuration. |
| Primary cohort | Pak Angels AI training graduates and comparable first-time AI builders. |
| Delivery posture | Closed pilot first; one supported template; managed defaults; measurable release gates. |
| Recommended duration | 10 weeks, followed by a two-week closed-pilot decision window. |

MILESTONE DEFINITION M0 is complete only when a new non-technical participant can reach a healthy share link without facilitator intervention or exposure to infrastructure concepts.

# Decision Summary

Build one production-quality vertical slice—not a broad builder with shallow integrations.

Use Aqlio-managed AI capacity, versioning, retrieval, and deployment during the closed pilot.

Allow no arbitrary agent actions, arbitrary code, external tools, or advanced configuration in M0.

Measure user confidence and useful deployment, not merely account creation or generated output.

# 1. Milestone Charter

# 1.1 Objective

Prove that Aqlio can hide sophisticated AI and cloud infrastructure behind a simple, affordable, dependable experience. A user brings a small set of documents, previews an assistant that answers from those documents with citations, deploys it, and shares a controlled link.

# 1.2 Supported template

TEMPLATE Ask My Documents — create a private or shareable assistant that answers questions from uploaded PDF, DOCX, or TXT files and shows the supporting source passages.

# 1.3 In scope

Registration, managed authentication, and automatic personal workspace.

Project creation from one named template.

Upload, validation, extraction, chunking, embedding, and indexed retrieval for supported documents.

Guided assistant name, purpose, welcome message, and example questions.

Preview with citations and three guided test questions.

Automatic version save, one-click deployment, health verification, and Aqlio share link.

Private-by-default sharing, link visibility controls, deployment history, usage summary, and portfolio suggestion.

Metering, budgets, policy, audit, observability, deletion, and support operations.

# 1.4 Explicitly out of scope

GitHub connection or repository management in the user journey.

Railway branding, deployment provider selection, environment variables, domains, or runtime sizing.

User-supplied API keys or model/provider selection.

Workflow canvas, multi-agent teams, arbitrary tools, external business-system actions, or custom code.

Paid plans, open marketplace, client contracting, public trust scoring, or enterprise governance.

Images, audio, video, scanned-document OCR, websites, and data connectors unless separately approved.

# 1.5 M0 success statement

A participant who describes themselves as non-technical can sign up, create the supported project, add valid documents, verify useful cited answers, deploy, and open the shared experience in a new browser session—all without encountering an infrastructure term or needing facilitator rescue.

# 2. The User Experience Contract

# 2.1 The only primary journey

| Step | Screen promise | Primary action | Completion signal |
| --- | --- | --- | --- |
| 1. Welcome | One clear way to begin. | Create my first project | Project setup opens within 30 seconds. |
| 2. Create Project | Name the outcome, not the technology. | Use Ask My Documents | Project and private workspace are ready. |
| 3. Add Documents | Explain supported files and privacy plainly. | Add documents | Every file is Ready or has a useful correction. |
| 4. Personalize | Make the assistant recognizable. | Save and preview | Welcome text and examples appear. |
| 5. Preview | Ask questions and verify sources. | Run guided tests | Three tests complete; user confirms usefulness. |
| 6. Deploy | Explain what will become accessible. | Deploy | Status becomes Running. |
| 7. Share | Give a link and visibility choice. | Copy link | Link opens with intended access. |
| 8. Next Step | Celebrate evidence and offer improvement. | Add to Portfolio / Improve | Evidence is reviewed or next action chosen. |

# 2.2 Language rules

| Avoid | Use |
| --- | --- |
| Create repository | Create project |
| Configure RAG pipeline | Add documents |
| Choose embedding model | Prepare documents |
| Select LLM/provider | Use AI |
| Configure deployment | Deploy |
| Railway deployment succeeded | Your assistant is running |
| Commit / release | Saved version |
| Token quota | AI usage |
| Vector index failed | We could not prepare this document; try the suggested fix |

# 2.3 Progressive disclosure

M0 has one experience level: guided beginner. Technical diagnostics are available only to authorized support and engineering roles. The product may show document status, deployment status, usage, and privacy implications, but never vendor configuration.

30-SECOND RULE On every screen, the next meaningful action is visually dominant and understandable without documentation.

# 3. Screen-by-Screen Requirements

# 3.1 Welcome and automatic Workspace

Email/social sign-in through managed authentication.

Automatic personal workspace, starter entitlement, usage ledger, and default private settings.

One recommended card: “Ask questions from my documents.”

No provider, credential, GitHub, or pricing setup.

# 3.2 Create Project

Required: project name. Optional: one-sentence purpose and intended audience.

Pre-fill a useful name from the purpose; user can edit it.

Create project, initial version, asset namespace, and audit event atomically.

# 3.3 Add Documents

Drag/drop and file picker; PDF, DOCX, TXT only for M0.

Show supported size/count limits before upload.

Per-file states: Uploading, Preparing, Ready, or Needs Attention.

Plain-language errors for password-protected, empty, unsupported, oversized, duplicated, or extraction-failed files.

Require at least one Ready document before Preview.

# 3.4 Personalize

Assistant name, short description, welcome message, and up to three suggested questions.

Aqlio proposes defaults derived from the project purpose and documents.

No system-prompt editor; safe instructions are assembled internally.

# 3.5 Preview and guided validation

Chat preview answers only from authorized project documents.

Every substantive answer shows source filename and supporting passage reference.

Provide three generated test questions plus “Ask my own question.”

User must confirm “The answers are useful” or improve documents/settings before deployment.

Clear safe response when evidence is insufficient.

# 3.6 Deploy

Preflight checks documents, saved version, visibility, limits, and policy.

Single Deploy button; states: Preparing, Deploying, Checking, Running, Needs Attention.

Preserve project state on timeout, provider error, or allowance boundary.

Running state includes Open, Copy Link, and Sharing Settings.

# 3.7 Share and Portfolio

Private by default; options: Only me or Anyone with the link for closed pilot.

Warning that link-access users can ask questions against published project documents.

Portfolio suggestion shows project name, purpose, deployment date, and verified running status.

User reviews before publishing evidence.

# 4. Hidden System Behavior

The following components are mandatory even though they remain outside the user’s mental model.

| Visible action | Hidden orchestration | Required record |
| --- | --- | --- |
| Sign up | Managed authentication, workspace creation, entitlement initialization. | user, workspace, membership, allowance ledger |
| Create project | Project aggregate, private storage namespace, initial immutable version. | project, project_version, audit_event |
| Add documents | Malware/type checks, extraction, chunking, embeddings, indexing. | asset, ingestion_job, chunk, embedding reference |
| Ask question | Authorization, retrieval, prompt assembly, model routing, citation mapping, metering. | builder_run, retrieval trace, usage_event, safe audit metadata |
| Deploy | Release creation, secret injection, runtime provisioning, health check, URL mapping. | release, deployment, health_check, provider reference |
| Share | Visibility policy, access enforcement, activity and evidence event. | share_policy, access_event, portfolio suggestion |

# 4.1 Required adapters

AIProviderAdapter: one primary managed provider, one policy-approved fallback, normalized streaming, usage, error, and citation metadata.

DeploymentAdapter: Railway implementation hidden behind normalized deploy, status, health, URL, and rollback operations.

StorageAdapter: private objects, signed access, deletion, and lifecycle rules.

NotificationAdapter: in-product completion/failure messages; email only where it materially improves recovery.

SourceControlAdapter: interface may exist, but no GitHub implementation is required for M0 user projects.

# 4.2 Smart defaults

| Decision | M0 default | Override |
| --- | --- | --- |
| AI model/provider | Policy-selected managed route. | Support/engineering configuration only. |
| Retrieval settings | Template-tuned chunking, top-k, citation threshold. | Template configuration only. |
| Deployment target | Managed Railway project through adapter. | None in user interface. |
| Visibility | Only me. | Anyone with link after explicit confirmation. |
| Versioning | Automatic immutable version on meaningful save/deploy. | Restore prior version; no Git terminology. |
| Budget | Daily user allowance plus per-run and per-project limits. | Administrative configuration only. |

# 5. Functional Acceptance Criteria

# 5.1 End-to-end happy path

☐ A new user creates an account and reaches the recommended template within 30 seconds.

☐ The user creates a project with no infrastructure configuration.

☐ At least one valid document reaches Ready status.

☐ Preview produces grounded answers with correct source references.

☐ Insufficient evidence produces an honest, helpful response rather than an invented answer.

☐ The user completes three guided tests and confirms usefulness.

☐ Deploy reaches Running and returns a stable Aqlio URL.

☐ The link opens in a clean browser session with the configured visibility behavior.

☐ A reviewed portfolio suggestion is created from deployment evidence.

☐ The entire visible journey contains none of the prohibited infrastructure terms.

# 5.2 Failure and recovery

☐ Unsupported or invalid files fail individually without losing valid files.

☐ Ingestion retries are idempotent and cannot create duplicate searchable content.

☐ Provider timeout preserves the user question and offers retry.

☐ Deployment retry cannot create uncontrolled duplicate runtimes.

☐ Allowance exhaustion never loses project state or a completed answer.

☐ Rollback returns to the previous healthy release.

☐ Deletion removes source objects and derived retrieval data according to policy.

☐ Support can trace a user action across application, job, provider, deployment, and usage records without seeing secrets.

# 5.3 Accessibility and responsive behavior

☐ Core flow is keyboard operable with visible focus.

☐ Controls have accessible names and status updates are announced appropriately.

☐ Color is not the only carrier of state.

☐ Upload and error instructions are understandable at plain-language reading level.

☐ Core journey is usable on common laptop and tablet widths; mobile supports review and sharing.

# 6. Non-Functional and Safety Requirements

| Area | M0 requirement | Release evidence |
| --- | --- | --- |
| Security | Private by default, least privilege, encrypted secret references, file validation, rate limiting. | Threat review and security checklist approved. |
| Privacy | Content excluded from product analytics; provider handling disclosed; deletion path documented. | Privacy review and deletion test. |
| Grounding | Answers constrained to retrieved evidence with citations and safe insufficient-evidence behavior. | Evaluation set meets thresholds. |
| Cost | Per-request, daily-user, and project-level hard limits; reconciled usage ledger. | Budget tests and pilot cost dashboard. |
| Reliability | Idempotent jobs, observable status, reconciliation, backup/restore, rollback. | Failure-injection and restore evidence. |
| Performance | Responsive UI; bounded ingestion and answer times communicated honestly. | P50/P95 pilot measurements. |
| Abuse | Upload limits, content scanning, prompt-injection defenses, sharing rate limits. | Abuse test suite and response runbook. |
| Audit | Sensitive access, sharing, deploy, deletion, and admin changes recorded. | Audit-event coverage report. |

# 6.1 Initial operating limits

The following are recommended pilot defaults and must remain administratively configurable: five documents per project; 10 MB per file; 25 MB total extracted content; three active projects per user; one active deployment per project; bounded answer context; bounded retries; daily managed-AI allowance; and hard deployment/runtime budget. Final values should be set after measured cost tests, not treated as permanent product promises.

# 7. Success Metrics and Release Gates

| Metric | Definition | Closed-pilot gate |
| --- | --- | --- |
| Next-step clarity | Participant identifies correct first action within 30 seconds. | ≥ 80% |
| First preview completion | Activated participants reaching a valid preview. | ≥ 70% |
| Useful deployment | Activated participants reaching Running and rating result useful. | ≥ 60% overall |
| Non-technical completion gap | Difference from technical participants. | ≤ 15 percentage points |
| Guided time to deployment | Median active time for valid inputs. | ≤ 45 minutes |
| Deployment reliability | Deploy requests reaching healthy state without staff action. | ≥ 90% |
| Grounded-answer quality | Evaluation answers meeting correctness/citation rubric. | ≥ 85% |
| First-week return | Activated participants returning within seven days. | ≥ 35% |
| Confidence | “I can create or improve an AI solution.” | ≥ 4.0 / 5 |
| Cost guardrail | Managed cost per useful deployment. | Within approved pilot budget |
| Security/privacy | Severity-1 incidents. | 0 |

# 7.1 Instrumentation

signup_completed, workspace_created, template_selected, project_created

document_uploaded, document_ready, document_failed, ingestion_completed

preview_question_asked, cited_answer_returned, guided_test_completed, usefulness_confirmed

deployment_requested, deployment_running, deployment_failed, link_opened, project_shared

portfolio_suggested, portfolio_published, allowance_threshold_reached, deletion_requested

Product events must contain identifiers and safe operational metadata, not raw prompts, extracted document text, secrets, or generated answers unless a separately approved diagnostic mode is explicitly enabled.

# 8. Delivery Backlog

| Epic | Outcome | Key stories | Exit evidence |
| --- | --- | --- | --- |
| E0 Foundations | Safe deployable skeleton. | Design system; auth; workspace; project aggregate; events; CI/CD; observability. | Staging environment and traceable smoke test. |
| E1 Guided Project | User starts with one clear template. | Welcome; template card; project setup; smart defaults. | Moderated prototype passes clarity gate. |
| E2 Document Preparation | Documents become searchable safely. | Upload; validation; extraction; indexing; status; deletion. | Corpus tests and failure recovery pass. |
| E3 Preview & Validation | User sees grounded value before deploy. | Chat; citations; test questions; insufficient evidence; save version. | Quality evaluation passes threshold. |
| E4 Deploy & Share | One action creates a usable link. | Preflight; release; adapter; health; URL; privacy; rollback. | Clean-session link test passes. |
| E5 Portfolio & Next Step | Success becomes evidence. | Suggestion; review; publish; improve prompt. | Evidence correctly links healthy deployment. |
| E6 Metering & Operations | Usage is bounded and supportable. | Ledger; allowances; budgets; admin config; alerts; runbooks. | Cost and incident drills pass. |
| E7 Pilot Readiness | Closed cohort can use the product safely. | Onboarding; consent; feedback; dashboards; support process. | Go/no-go review approved. |

# 8.1 Critical dependency order

Identity/workspace and project/version records precede document ingestion.

Storage, deletion, and authorization precede embeddings and retrieval.

Evaluated preview quality precedes deployment.

Deployment reconciliation and rollback precede portfolio verification.

Metering and budgets ship with provider calls, not after pilot usage begins.

# 9. Ten-Week Delivery Plan

| Week | Primary outcome | Demonstration |
| --- | --- | --- |
| 1 | Scope, journey, data handling, evaluation rubric, and operating limits locked. | Clickable happy-path prototype and architecture decision record. |
| 2 | Platform skeleton and design system operational. | Sign in → automatic workspace → create project in staging. |
| 3 | Upload and storage pipeline complete. | Valid/invalid files show correct statuses and deletion. |
| 4 | Extraction, chunking, embeddings, and retrieval complete. | Prepared documents return traceable passages. |
| 5 | Preview and citations complete. | Guided questions produce grounded cited answers. |
| 6 | Quality, safety, and usability iteration. | Evaluation threshold and moderated preview tests pass. |
| 7 | Deployment adapter and managed runtime complete. | Deploy → health check → Aqlio URL. |
| 8 | Sharing, rollback, portfolio, and usage summary complete. | Clean-session access and evidence flow. |
| 9 | Reliability, security, cost, deletion, and support hardening. | Failure drills, budget tests, backup/restore, runbooks. |
| 10 | Closed-pilot release candidate. | End-to-end acceptance and go/no-go review. |

# 9.1 Pilot decision window

Run a two-week closed pilot with 15–25 participants, intentionally including at least half who self-identify as non-technical. Observe sessions, collect task-level friction, review cost and quality daily, and make the public-beta decision only after the release gates are met.

# 10. Roles and Operating Cadence

| Role | Accountability |
| --- | --- |
| Product owner | Scope, user outcome, acceptance decisions, release gates. |
| Product designer | Guided flow, language, accessibility, moderated testing. |
| Tech lead | Architecture, module boundaries, adapters, delivery quality. |
| Frontend engineer | Workspace, project, builder, deployment, sharing interfaces. |
| Backend/AI engineer | Ingestion, retrieval, routing, citations, versions, metering. |
| Platform engineer | Runtime, deployment adapter, observability, backups, cost controls. |
| Security/privacy reviewer | Threats, permissions, data handling, deletion, audit. |
| Pilot lead/support | Cohort readiness, facilitation, feedback, incident escalation. |

# 10.1 Cadence

Daily engineering stand-up focused on blockers and working software.

Twice-weekly end-to-end demo using the same pilot scenario.

Weekly usability session with at least two target users beginning in Week 2.

Weekly cost, quality, reliability, and risk review beginning with the first live provider call.

Formal go/no-go at the end of Week 10 and after the two-week pilot.

# 11. Key Risks and Mitigations

| Risk | Early signal | Mitigation |
| --- | --- | --- |
| Answers appear authoritative but are unsupported. | Low citation correctness or user reports. | Evidence threshold, citations, honest abstention, evaluation corpus. |
| Document preparation feels slow or opaque. | Drop-off during ingestion. | Per-file progress, background jobs, notifications, realistic estimates. |
| Hidden defaults create unexpected cost. | Cost per preview/deployment rises. | Budgets, hard limits, caching, route policy, daily review. |
| Sharing exposes sensitive information. | Users misunderstand link access. | Private default, explicit confirmation, plain-language warning, revoke control. |
| Deployment provider state drifts. | Aqlio and runtime disagree. | Reconciliation jobs, idempotency, health checks, rollback. |
| Scope expands into a general builder. | New template/tool requests enter sprint. | M0 change control; defer unless required for release gate. |
| Technical users pressure UI complexity. | Advanced controls appear in core screens. | Support diagnostics separate; preserve beginner contract. |

# 12. Go/No-Go Checklist

# 12.1 Product and experience

☐ The prohibited terms do not appear in the participant journey.

☐ The correct next action is clear within 30 seconds on every screen.

☐ At least the minimum useful-deployment and non-technical completion gates are met.

☐ All error states preserve work and give a useful recovery action.

# 12.2 Quality, safety, and operations

☐ Grounded-answer and citation evaluation passes.

☐ Authorization, private defaults, sharing, and deletion tests pass.

☐ Provider and deployment budgets and hard limits are active.

☐ Deployment reconciliation, rollback, backup, and restore are tested.

☐ Operational dashboards, alerts, ownership, and incident runbooks are ready.

☐ No unresolved severity-1 security, privacy, data-loss, or billing defect remains.

# 12.3 Pilot readiness

☐ Pilot cohort, consent, instructions, support channel, and escalation owners are confirmed.

☐ Instrumentation is validated without collecting prohibited content.

☐ Feedback survey measures usefulness, confidence, clarity, and likelihood to return.

☐ A documented rollback or pilot suspension decision can be executed immediately.

RELEASE DECISION Ship M0 to a closed pilot when every safety and operational gate passes and the end-to-end journey works reliably. Expand beyond the pilot only when the outcome metrics—not schedule pressure—justify it.

# Appendix A — Canonical Pilot Scenario

A participant creates “Employee Handbook Assistant,” uploads a small employee handbook and benefits guide, accepts the suggested welcome message and questions, verifies answers about leave and benefits with source citations, deploys the assistant privately, changes access to Anyone with the link after reading the warning, opens the link in a private browser window, and adds the verified deployment to a portfolio.

# Expected visible labels

Create my first project

Ask My Documents

Add documents

Preparing documents

Preview

The answers are useful

Deploy

Your assistant is running

Copy link

Sharing settings

Add to Portfolio

Improve

# Expected invisible implementation

Managed authentication and automatic workspace provisioning.

Private object storage, extraction, embeddings, vector retrieval, and citation mapping.

Policy-selected AI provider and model with fallback, budget, and metering.

Immutable project/release versions and idempotent background jobs.

Railway deployment through DeploymentAdapter, health verification, URL mapping, and rollback.

Audit, analytics, privacy, retention, deletion, and support traces.

# Appendix B — Architectural Alignment

Figure 1. M0 implements one thin vertical path through the approved MVP architecture.

M0 does not weaken the long-term architecture. It deliberately exercises Workspace, Projects, AI Builder, Deploy, Portfolio, AI Provider Adapter, Deployment Adapter, storage, PostgreSQL/pgvector, workers, events, observability, cost intelligence, policy, and audit through one understandable customer outcome.

Appendix C:

This first version establishes:

- “Ask My Documents” as the first supported template

- The complete non-technical user journey

- Screen-by-screen requirements and language rules

- Hidden orchestration and smart defaults

- Functional, safety, privacy, reliability, and accessibility criteria

- Delivery epics and dependencies

- A ten-week implementation schedule

- Closed-pilot success metrics and release gates

- Go/no-go checklist and canonical pilot scenario

- Alignment with the approved MVP architecture

The 15-page document passed rendered-layout and accessibility checks.